## Sheet1
Start Date 17/02/2025 | Current Status | WEEK 1 | WEEK 2 | WEEK3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16
Update Project Work Plan/LR/SRS/SDD | Completed | bar: WEEK 1 to WEEK 5
Test Plan Document | In Progress | bar: WEEK 5 to WEEK 7
Midterm Interactive Demo | Not Started | bar: WEEK 8
Final Product 1st Release | In Progress | bar: WEEK 1 to WEEK 11
User Manual | Not Started | bar: WEEK 12
Project Report / Test Results / Project Tracking Form | Not Started | bar: WEEK 13
ProjecProject Poster, Updated Project Webpage, Demo Videot Webpage | Not Started | bar: WEEK 14
Presentation | Not Started | bar: WEEK 15 to WEEK 16