## Sheet1
Start Date 30/09/2024 | Current Status | WEEK 1 | WEEK 2 | WEEK3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16
Team Setup | Completed | bar: WEEK 1
Project Proposal Form | Completed | bar: WEEK 2
Project Selection Form | Completed | bar: WEEK 2
GitHub Repository | Completed | bar: WEEK3
Project Work Plan | Completed | bar: WEEK 4
Literature Review | Completed | bar: WEEK 5 to WEEK 6
Software Requirements Specification | Completed | bar: WEEK 7 to WEEK 10
Project Webpage | Completed | bar: WEEK 10 to WEEK 11
Software Design Description | Completed | bar: WEEK 11 to WEEK 12
Project Report / Project Tracking Form | In progress | bar: WEEK 12 to WEEK 13
Presentation | Not Started | bar: WEEK 14 to WEEK 16